## WBS
WBS ID | Phase | Task | Deliverable | Owner | Est. Duration | Status
1.0 | Requirements Engineering | Elicit and document FR/NFR from scenario | Requirements_SE.xlsx | Student | 1 day | Complete
1.1 | Requirements Engineering | Build Requirements Traceability Matrix (RTM) | RTM_Table.xlsx | Student | 0.5 day | Complete
2.0 | Design | Model actors and use cases (UML Use-Case Diagram) | UseCase_Diagram.pdf | Student | 1 day | Complete
2.1 | Design | Write use-case flow (main + alternate scenario) | Use_Case_Flow.docx | Student | 0.5 day | Complete
2.2 | Design | Design system architecture (components, data, integrations) | Architecture_Diagram.pdf | Student | 1 day | Complete
3.0 | Project Setup | Create and configure GitHub repository | GitHub repo + screenshot | Student | 0.5 day | Complete
3.1 | Project Setup | Create and configure Jira project/board | Jira screenshot | Student | 0.5 day | Pending
4.0 | Documentation | Write Software Requirements Specification (SRS) | SRS.docx | Student | 1 day | Complete
4.1 | Documentation | Build Work Breakdown Structure (this document) | WBS.xlsx | Student | 0.5 day | Complete
5.0 | AI-Assisted Development | Generate sample code with GitHub Copilot | Code screenshot / repo link | Student | 1 day | Pending
6.0 | Software Testing | Run 4 provided test cases on game application | Test run notes | Student | 0.5 day | Pending
6.1 | Software Testing | Diagnose and fix identified bug (vibe coding) | Code patch | Student | 1 day | Pending
6.2 | Software Testing | Retest and confirm fix; share fixed repo link | Repository link | Student | 0.5 day | Pending